## Sheet1
Sr. No. | Points | Suggested By | Status | Developer Name | Estimated Date | Revised Dates
1 | in mail add cr no: + subject | gary and noopur | done 12 Oct 2015 | aaliya
2 | Create exe file for sending mail to users for pending cr. | noopur |  | aaliya | 2015-10-14 | 16-10-2015/End of the day
3 | Data for CR register should come from vw_CRRegisterData. | aaliya and mushfiq | done 12 Oct 2015 | aaliya
4 | check on server for Micosoft ACE Oledb 12.0 | error | done 12 Oct 2015 | mushfiq and aaliya
5 | In mdc ITAT, write validation on server side for end date,uat date and itat date, don’t allow null. | error | done |  | 2015-10-14 | 15-10-2015/End of the day
6 | send mail to initiator after creating new CR. | mdc team |  |  | Not to do, as discussed with noopur mam
7 | task deletion is not working | error |  |  | 2015-10-20
8 | MDC CR , Closing issue | error |  | mushfiq | 2015-10-20
9 | work flow related issues | error |  | mushfiq | 2015-10-20
10 | Export to excel all reports. | mushfiq |  | aaliya | 2015-10-19
11 | all change request option does not show all cr raised by user | error |  |  | 2015-10-19
12 | Sub ITFH functionality | gary and noopur | done 12 Oct 2015 | aaliya
13 | division and sub division - data clean | mdc team |  | aaliya
14 | itat date and end date is submitted blank. | error | done |  | 2015-10-14 | 15-10-2015/End of the day
15 | copy same data (esttimated days,start date,end date,description) of phase in first row of phase task. | mushfiq | done 12 Oct 2015 | aaliya
16 | Plateform field in vendor details should be same as selected sub module. | mushfiq | done 12 Oct 2015 | aaliya
17 | if session expired then system should show any msg before refreshing any page. | Rajesh Shigwan | done |  | 2015-10-14 | 15-10-2015/End of the day
18 | In phase, set phase desc default value as "Phase 1" and task name as "Task 1".-set phase 1=module, task-1st 50 characters of subject. | gary | done |  | 2015-10-14
19 | in phase, set itat date same as end date +1. | gary | done 13 Oct 2015 |  | 2015-10-13
20 | add functionality of UAT not required. | noopur |  |  | 2015-10-15 | 17-10-2015/End of the day
21 | don’t allow decimal in estimated days. | validation | done | aaliya | 2015-10-14
22 | data sync from oracle. |  | done |  | 2015-10-13
23 | Basis - email content, with transportremarks | noopur | done
24 | Exception report-all reports. |  |  |  | 2015-10-22
25 | oaap report | noopur
26 | all reqquest should be seen only of that user who is in cr system |  |  | aaliya
27 | for all ctegory set-selected vendor for one row / prefered vendor |  | done | aaliya | 2015-10-14
28 | set position of calendar in itat and uat date. |  |  |  | 2015-10-21
29 | assign to team drpdwn, for assign to itfh. |  | done |  | 2015-10-15
30
| filter in cr register | shigwan and gary |  | aaliya | 2015-10-16